## Hoja1
Roadmap
Day
| Monday | Tuesday | Wednesday | Thursday | Friday | Monday
Sprint | 8 | 9 | 10 | 11 | 12 | 15
1 | 1.a Git installed in local pc
1.b Git credentials
1.c Connection to a hub
1.d Company permission granted
2.a Create a GitHub account with corporate email
2.b Set up security authentication(s)
2.c Get invited to the company’s repository
3.a The repository must be cloned locally.
3.b Use of basic commands: git add, git commit, git push, git pull
2 |  |  | 4.a Create a new branch with a descriptive name
4.b Make changes to files in the branch without affecting the main branch
4.c Commit changes with meaningful messages
4.d Push the branch to the remote repository for review.
5.a Submit a pull request with changes
5.b Receive and view feedback from a team member
5.c Receive final approval
3 |  |  |  |  | 6.a Complete the set-up process on the onboarding
6.b Practice on company tools and processes
6.c Receive confirmation from the team lead that onboarding is complete